## Non Consulting
Description (Value cannot exceed 250 Characters) | Reference No. | Category - Sourcing | Sourcing Method | Type of Competition | Estimated Amount in US$ | Financed By | Request Submission Date | Invitation Date | Opening Date | Evaluation Date | Approval Date | Opening of Financial Proposal | Combined Evaluation | Approval Date | Contract Vetting | Contract Signing
NON CONSULTING
Cybersecurity Training Programs: Regularly conduct cybersecurity awareness and training programs for all staff to mitigate human error risks. | AfCFTA/AHRMD/NC/001 | NC | RFQ | OC | 25000 | IPs | Q2, Q3, Q4 | 2025-04-03 | 2025-05-05 | 2025-05-11 | 2025-03-17 | 2025-04-03 | 2025-04-10 | 2025-04-15 | 2025-04-21 | 2025-05-01
Workshop and training (Conduct regular reviews of plans to ensure they remain relevant and effective) soft skills eg Emotional intelligence,conflict management, change management/decision makinG | AfCFTA/AHRMD/NC/002 | NC | RFQ | OC | 9164.19 | IPs | Q1 | 2025-04-06 | 2025-05-05 | 2025-05-13 | 2025-05-19 | 2025-06-07 | 2025-06-14 | 2025-06-18 | 2025-06-25 | 2025-07-05
Collaborative Platforms: Integrate collaborative platforms for seamless document sharing and project management (Like microsoft teams) | AfCFTA/AHRMD/NC/003 | NC | RFQ | OC | 10000 | PAI | Q3 | 2025-07-02 | 2025-08-01 | 2025-08-06 | 2025-08-12 | 2025-08-29 | 2025-09-05 | 2025-09-09 | 2025-09-16 | 2025-09-30
Training Workshops(Implementation of SOP'S, Implementation of disaster recovery plan | AfCFTA/AHRMD/NC/004 | NC | RFQ | OC | 12435 | IPs | Q2 | 2025-04-02 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-06-04 | 2025-06-11 | 2025-06-16 | 2025-06-23 | 2025-07-08
Virtual Mentorship Programs: Establish virtual mentorship programs to facilitate knowledge sharing and professional development. | AfCFTA/AHRMD/NC/005 | NC | DIR | LC | 10000 |  | Q3 | 2025-07-04 | 2025-08-04 | 2025-08-12 | 2025-08-19 | 2025-09-04 | 2025-09-11 | 2025-09-16 | 2025-09-22 | 2025-10-06
SAP training and Workshops (Material Management and Supply Chain Management Module | AfCFTA/AHRMD/NC/006 | NC | DIR | LC | 10000 | MS | Q4 | 2025-10-06 | 2025-11-03 | 2025-11-11 | 2025-11-18 | 2025-12-02 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2026-01-06
SAP training and Workshops (HR and Finance Management | AfCFTA/AHRMD/NC/007 | NC | DIR | LC | 10000 | MS | Q4 | 2025-10-07 | 2025-11-04 | 2025-11-12 | 2025-11-19 | 2025-12-03 | 2025-12-11 | 2025-12-18 | 2025-12-28 | 2026-01-12
Virtual Recruitment Fairs: Host virtual recruitment fairs to attract a diverse pool of candidates | AfCFTA/AHRMD/NC/011 | NC | RFQ | OC | 10000 | IPs | Q1, Q2, Q3, Q4 | 2025-04-13 | 2025-05-13 | 2025-05-19 | 2025-05-27 | 2025-06-14 | 2025-06-21 | 2025-04-28 | 2025-05-06 | 2025-05-16
Employee Wellness Programs: Integrate wellness programs into performance management to support employee well-being | AfCFTA/AHRMD/NC/014 | NC | RFQ | OC | 15000 | IPs | Q1, Q2, Q3, Q4 | 2025-04-13 | 2025-03-13 | 2025-03-19 | 2025-04-27 | 2025-05-14 | 2025-05-21 | 2025-05-28 | 2025-06-06 | 2025-06-20
Workshop and training for AfCFTA Culture | AfCFTA/AHRMD/NC/018 | NC | RFQ | OC | 20000 | PAI | Q3 | 2025-07-07 | 2025-08-05 | 2025-08-12 | 2025-08-20 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06
Recognition and Reward Programs: Implement programs to recognize and reward employees who embody the desired culture | AfCFTA/AHRMD/NC/019 | NC | RFQ | OC | 15000 | PAI | Q1, Q2, Q3, Q4 | 2025-04-12 | 2025-03-12 | 2025-03-18 | 2025-04-25 | 2025-05-10 | 2025-04-17 | 2025-04-24 | 2025-05-02 | 2025-05-16
Architect fees | AfCFTA/AHRMD/NC/020 | NC | RFQ | OC | 45000 | IPs | Q1, Q2, Q3, Q4 | 2025-04-17 | 2025-03-18 | 2025-03-25 | 2025-04-30 | 2025-05-16 | 2025-05-23 | 2025-05-28 | 2025-06-05 | 2025-06-15
Training on the modules on MBRS (onboarding and off boarding) | AfCFTA/AHRMD/NC/021 | NC | DIR | LC | 65000 | IPs | Q4 | 2025-10-01 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-12-05 | 2025-12-11 | 2025-12-18 | 2025-12-29 | 2026-01-12
Training for additional modules on SAP (Activation of open text) | AfCFTA/AHRMD/NC/022 | NC | RFQ | OC | 30000 | IPs | Q4 | 2025-10-07 | 2025-11-04 | 2025-11-12 | 2025-11-20 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-13
Framework Contract for Travel Management Services (TMS) | AfCFTA/AHRMD/NC/023 | NC | RFQ | OC |  |  |  | 2025-11-09 | 2025-12-09 | 2025-12-12 | 2025-12-15 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21
Media Training workshop for AfCFTA Leadership | AfCFTA/COMMS/NC/001 | NC | RFQ | OC | 38040 | MS | 2025-02-15 | 2025-04-20 | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-28
Traditional media advertorial for the promotion of AfCFTA flagship initiatives, education on benefits of Protocols and sharing of updates on progress of implementation | AfCFTA/COMMS/NC/002 | NC | RFQ | OC | 30000 | MS | 2025-03-01 | 2025-04-10 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-17
Conduct Island Advocacy programmes | AfCFTA/COMMS/NC/003 | NC | RFQ | OC | 7177 | MS | 2025-04-01 | 2025-04-07 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-16
Communications campaign for celebration of Africa Day | AfCFTA/COMMS/NC/004 | NC | RFQ | OC | 36000 | MS | 2025-05-15 | 2025-05-20 | 2025-06-20 | 2025-06-27 | 2025-07-04 | 2025-07-22 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-26
Conduct strategic communications consultations with National Implementation Committees | AfCFTA/COMMS/NC/006 | NC | RFQ | OC | 34520 | MS | 2025-03-01 | 2025-04-05 | 2025-04-07 | 2025-04-15 | 2025-04-22 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-17
Undertake media workshop trainings in all 5 regions and in the diaspora | AfCFTA/COMMS/NC/007 | NC | RFQ | OC | 35250 | MS | 2025-04-01 | 2025-04-07 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-14
Capacity building for Communications staff | AfCFTA/COMMS/NC/008 | NC | RFQ | OC | 38096 | MS | 2025-03-01 | 2025-04-10 | 2025-04-10 | 2025-04-17 | 2025-04-24 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-17
Conduct Regional roadshows towards AfCFTA initiatives to support the implementation of the AfCFTA Agreement | AfCFTA/COMMS/NC/009 | NC | RFQ | OC | 28639.2 | MS | 2025-04-15 | 2025-04-21 | 2025-05-21 | 2025-05-28 | 2025-06-04 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-24
Production of awareness creation videos and podcast to promote the AfCFTA and share information and updates on progress made in implementation | AfCFTA/COMMS/NC/010 | NC | RFQ | OC | 5000 | MS | 2025-02-01 | 2025-04-06 | 2025-03-07 | 2025-03-13 | 2025-04-20 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-09
Improved monitoring and evaluation systems in assessing communication efforts to mainstream and promote the provisions and benefits of the AfCFTA to all stakeholders | AfCFTA/COMMS/NC/011 | NC | RFQ | OC | 10000 | MS | 2025-01-15 | 2025-04-21 | 2025-02-24 | 2025-03-03 | 2025-04-10 | 2025-04-25 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-29
Two Communications Briefing consultations to RECs through Public Relations Departments | AfCFTA/COMMS/NC/012 | NC | RFQ | OC | 42451 | MS | 2025-04-10 | 2025-04-15 | 2025-05-15 | 2025-05-22 | 2025-05-29 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-17
2nd Meeting of the Sub - Committee on Mutual Recognition of Professional Qualifications (SCMRPQ) | AfCFTA/TIS/NC/001 | NC | RFQ | OC | 36708 |  | 2025-10-31 | 2025-09-16 | 2025-09-22 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-10-01 | 2025-10-02 | 2025-10-03
7th Meeting of the Sub Committee on Regulatory Frameworks (SCRF) | AfCFTA/TIS/NC/003 | NC | RFQ | OC | 75000 |  | 2025-08-15 | 2025-08-01 | 2025-08-05 | 2025-08-06 | 2025-08-08 | 2025-08-09 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14
6th Meeting of the Sub Committee on Specific Commitments (SCSC) | AfCFTA/TIS/NC/005 | NC | RFQ | OC | 21600 |  | 2025-10-03 | 2025-09-16 | 2025-09-22 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-10-01 | 2025-10-02 | 2025-10-03
Stakeholder Engagement workshop on Education Services | AfCFTA/TIS/NC/008 | NC | RFQ | OC |  |  | 2025-05-16 | 2025-04-15 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27
Stakeholder Engagement workshop on Recreational, Cultrural and Sporting Services | AfCFTA/TIS/NC/009 | NC | RFQ | OC | 26800 |  | 2025-07-09 | 2025-06-10 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22
Stakeholder Engagement workshop on Construction Services | AfCFTA/TIS/NC/010 | NC | RFQ | OC |  |  | 21 August 2025 | 2025-07-25 | 2025-07-25 | 2025-06-01 | 2025-06-08 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-27
AfCFTA Regulatory Audit Workshop for Tunisia | AfCFTA/TIS/NC/011 | NC | RFQ | OC | 49666 |  | 2025-08-08 | 2025-04-26 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-28
1st Expert Group Meeting on the Draft AfCFTA Guidelines on Mutual Recognition Agreements (MRAs) | AfCFTA/TIS/NC/012 | NC | RFQ | OC | 36708 |  | 26 September 2025 | 2025-04-27 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-29
2nd Expert Group Meeting on the Draft AfCFTA Guidelines on Mutual Recognition Agreements | AfCFTA/TIS/NC/013 | NC | RFQ | OC | 51000 |  | 2025-11-12 | 2025-07-28 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16
Technical Working Session with Angola on the Finalisation of their Draft Schedule of Specific Commitments | AfCFTA/TIS/NC/016 | NC | RFQ | OC | 7600 |  | 25 June 2025 | 2025-05-01 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15
Capacity Building Workshop on Trade in Services under the AfCFTA and Technical Assistance to clean up of Mozambique’s initial TIS offer | AfCFTA/TIS/NC/017 | NC | RFQ | OC | 77401.5 |  | 2025-08-21 | 2025-07-02 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-08-03
Technical Assistance to Mozambique for the Finalisation of their DSSC and Support on AfCFTA Regulatory Audits | AfCFTA/TIS/NC/018 | NC | RFQ | OC | 77401.5 |  | 15 - 19 September 2025 | 2025-05-03 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-08-04
AfCFTA-WCO joint Capacity Building Programs | AfCFTA//CUSTM/NC/003 | NC | RFQ | OC | 150541 | AfDB | Jan. to Dec | 2025-04-21 | 2025-02-24 | 2025-03-03 | 2025-04-10 | 2025-04-25 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-29
Three hybrid Regional Capacity Building Workshops for Southern Africa, Northern and Western Africa, and Central Africa | AfCFTA//CUSTM/NC/004 | NC | RFQ | OC | 41734 | BADEA | Feb. April and Oct. | 2025-04-06 | 2025-03-05 | 2025-03-13 | 2025-04-19 | 2025-04-07 | 2025-04-14 | 2025-04-18 | 2025-04-25 | 2025-05-05
Three Virtual Regional Capacity Building Workshops for Eastern Africa, Western Africa, and Northern Africa | AfCFTA//CUSTM/NC/005 | NC | RFQ | OC | 28000 | AfDB | March, May, and Sept. | 2025-04-04 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-06-06
Train-the Trainer Program for SACU Member States on Rules of Origin | AfCFTA//CUSTM/NC/007 | NC | RFQ | OC | 72080 | WORLD BANK
Engage the schools/Institutes of Customs to develop a dedicated AfCFTA Customs curriculum | AfCFTA//CUSTM/NC/008 | NC | RFQ | OC | 26000 | SPAIN | Jan-Dec. | 2025-04-16 | 2025-02-17 | 2025-02-24 | 2025-04-03 | 2025-04-18 | 2025-04-25 | 2025-05-01 | 2025-05-08 | 2025-05-22
Identify and engage key African private Sector Associations and develop dedicated trainings to them on AfCFTA customs-related topics | AfCFTA//CUSTM/NC/009 | NC | RFQ | OC | 26268 | SPAIN | Jan to Dec. | 2025-04-20 | 2025-02-20 | 2025-02-27 | 2025-04-07 | 2025-04-21 | 2025-04-28 | 2025-05-04 | 2025-05-11 | 2025-05-25
Three (3) Benchmarking of E-CO Business Process and assess State Parties’ preparedness and digital maturity for piloting | AfCFTA//CUSTM/NC/010 | NC | RFQ | OC | 90000 | WORLD BANK | Jan. and Feb. | 2025-04-22 | 2025-02-24 | 2025-03-03 | 2025-04-10 | 2025-04-24 | 2025-05-01 | 2025-05-07 | 2025-05-14 | 2025-05-28
WCO Support on Business Process Model | AfCFTA//CUSTM/NC/011 | NC | RFQ | OC | 13000 | WORLD BANK | Jan. | 2025-04-16 | 2025-02-17 | 2025-02-24 | 2025-04-03 | 2025-04-18 | 2025-04-25 | 2025-05-01 | 2025-05-08 | 2025-05-22
3rd E-CO TWG Meeting for adoption of the E-CO PBA and propose list of pilot countries and consider the ToR for the selection Technology Provider | AfCFTA//CUSTM/NC/012 | NC | RFQ | OC | 30000 | WORLD BANK | March | 2025-04-03 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-06-05
Benchmark of Technology for the AfCFTA E-CO System, | AfCFTA//CUSTM/NC/013 | NC | RFQ | OC | 20650 | WORLD BANK | May and Dec. | 2025-05-01 | 2025-06-02 | 2025-06-09 | 2025-06-17 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-08
Coordination meeting to support the establishment of the Djibouti-Ethiopia Management Corridor Authority and discuss the establishment of Galafi OSBP. And Trans KALAHARI Corridors; | AfCFTA//CUSTM/NC/014 | NC | RFQ | OC | 70435 | WORLD BANK | April | 2025-04-02 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-06-04 | 2025-06-11 | 2025-06-16 | 2025-06-23 | 2025-07-08
Field mission to th:e (1) West African maritime corridor; (2) Liberia-Sera Leone-Guinea Corridor; (3) Asia Corridor (China -Mongolia Economic Corridor; | AfCFTA//CUSTM/NC/015 | NC | RFQ | OC | 74750 | AFREXIMNBANK | Feb., June, Sept. and Nov. | 2025-04-06 | 2025-03-07 | 2025-03-13 | 2025-04-20 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-09
Support the implementation of the Simplified Trade Regime (STR) in the selected State Parties | AfCFTA//CUSTM/NC/017 | NC | RFQ | OC | 94090 | WORLD BANK | Nov. | 2025-11-04 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-09
Support the implementation of the Authorized Economic Operator (AEO) in two (2) State Parties | AfCFTA//CUSTM/NC/018 | NC | RFQ | OC | 101650 | AfDB | Nov. | 2025-11-07 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-10
Support the establishment of FastTrack Lane for the clearance of urgent and relief goods such as food and pharmaceuticals | AfCFTA//CUSTM/NC/019 | NC | RFQ | OC | 72710 | AFREXIMNBANK | Nov. | 2025-11-11 | 2025-12-09 | 2025-12-16 | 2025-12-23 | 2026-01-09 | 2026-01-16 | 2026-01-23 | 2026-01-30 | 2026-02-13
Awareness campaigns for Customs Officials and others stakeholder on Trade Facilitation Measures along the Abidjan Lagos Corridors | AfCFTA//CUSTM/NC/020 | NC | RFQ | OC | 67030 | AfDB | April | 2025-04-03 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-07-07
Engagement mission to Algeria to support establishment of its National Committee on Trade Facilitation | AfCFTA//CUSTM/NC/021 | NC | RFQ | OC | 10000 | AfDB | July | 2025-07-09 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-10
2nd Meeting of the National Committee on Trade Facilitation | AfCFTA//CUSTM/NC/022 | NC | RFQ | OC | 30285 | AfDB | Oct. | 2025-10-01 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2026-01-05
Training Programme on the virtual platform for information exchanges | AfCFTA//CUSTM/NC/023 | NC | RFQ | OC | 7000 | AfDB | March | 2025-04-04 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-05-02 | 2025-05-09 | 2026-05-16 | 2025-05-23 | 2025-06-06
Develop a strategy for the implementation of regional single windows. | AfCFTA//CUSTM/NC/024 | NC | RFQ | OC | 78401 | WORLD BANK | April | 2025-04-08 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-10
Participation in international meeting on Trade Facilitation, Customs Cooperation and Transit. | AfCFTA//CUSTM/NC/025 | NC | RFQ | OC | 47115 | OSF | Jan. to Dec | 2025-01-20 | 2025-02-20 | 2025-02-27 | 2025-04-07 | 2025-04-21 | 2025-04-28 | 2025-05-04 | 2025-05-11 | 2025-05-25
Engagements with other international organisations (eg WCO, UNCTAD, UNECA, IBCC, IATA, ICS, IMO, ICAO, ICC, WTO) to identify and have inputs in developing best practices. | AfCFTA//CUSTM/NC/026 | NC | RFQ | OC | 54546 | WORLD BANK | Jan. to Dec | 2025-01-22 | 2025-02-24 | 2025-03-03 | 2025-04-10 | 2025-04-24 | 2025-05-01 | 2025-05-07 | 2025-05-14 | 2025-05-28
Support at least four Member States to use upgraded CMS (Customs Management System) to facilitate customs operations and exchange of data amongst themselves | AfCFTA//CUSTM/NC/027 | NC | RFQ | OC | 76160 | AfDB | Jan. to Dec | 2025-01-13 | 2025-02-10 | 2025-02-17 | 2025-04-24 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-14
Develop and roll-out the AfCFTA Continental Single Bond Transit Guarantee Scheme: Inaugural meeting of the AfCFTA Administative of the Single bond Guarantee and Piloting of Single bond guarantee | AfCFTA//CUSTM/NC/028 | NC | RFQ | OC | 78339 | WORLD BANK | Oct. and Dec. | 2025-10-07 | 2025-11-04 | 2025-11-12 | 2025-11-20 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-13
Facilitate harmonization of Customs Procedures in identified areas in the State Parties (HS, Unity of measurement) | AfCFTA//CUSTM/NC/030 | NC | RFQ | OC | 98980 | AFREXIMNBANK | Jan. to Dec | 2025-01-16 | 2025-02-17 | 2025-02-24 | 2025-04-03 | 2025-04-18 | 2025-04-25 | 2025-05-01 | 2025-05-08 | 2025-05-22
Collaborate with some AU Organ dealing with Trade Facilitation, Customs Cooperation and Transit ( Africa CDC, AUDA NEPAD, PIDA Programme, Peace and Security) | AfCFTA//CUSTM/NC/031 | NC | RFQ | OC | 32488 | EU-AUPPAP | Jan. to Dec | 2025-03-05 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-10
Facilitate cooperation through sharing of resources and skills amongst AfCFTA Customs. | AfCFTA//CUSTM/NC/032 | NC | RFQ | OC | 32555 | BADEA | Jan. to Dec | 2025-01-16 | 2025-02-17 | 2025-02-24 | 2025-04-03 | 2025-04-18 | 2025-04-25 | 2025-05-01 | 2025-05-08 | 2025-05-22
Consultations with stakeholder organisations in order to meet the requirements of business. | AfCFTA//CUSTM/NC/033 | NC | RFQ | OC | 47490 | BADEA | Jan. to Dec | 2025-01-21 | 2025-02-24 | 2025-03-03 | 2025-04-10 | 2025-04-25 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-05-29
Develop a Continental Digital platform for exchange of information and mutual cooperation amongst customs administrations | AfCFTA//CUSTM/NC/034 | NC | RFQ | OC | 40752 | AfDB | Jan. to Dec | 2025-01-16 | 2025-02-17 | 2025-02-24 | 2025-04-03 | 2025-04-18 | 2025-04-25 | 2025-05-01 | 2025-05-08 | 2025-05-22
Roll-out of the AfCFTA Transit Document Piloting of Single bond guarantee | AfCFTA//CUSTM/NC/035 | NC | RFQ | OC | 45000 | KOREA FUND | Jul. and Oct, | 2025-07-02 | 2025-08-01 | 2025-08-06 | 2025-08-12 | 2025-08-29 | 2025-09-05 | 2025-09-09 | 2025-09-16 | 2025-09-30
Facilitate the registration of means of transport in State Parties. | AfCFTA//CUSTM/NC/036 | NC | RFQ | OC | 52171 | BADEA | Jan. to Dec | 2025-01-16 | 2025-02-17 | 2025-02-24 | 2025-04-03 | 2025-04-18 | 2025-04-25 | 2025-05-01 | 2025-05-08 | 2025-05-22
Development of Certificate of approval of the means of transport | AfCFTA//CUSTM/NC/037 | NC | RFQ | OC | 24211 | AfDB | Jan. to June | 2025-01-03 | 2025-01-31 | 2025-02-07 | 2025-04-14 | 2025-04-28 | 2025-05-07 | 2025-05-14 | 2025-05-21 | 2025-06-04
Development of the Certified Declaration Form for examination of the means of transport. | AfCFTA//CUSTM/NC/038 | NC | RFQ | OC | 24211 | AfDB | Jan. | 2025-01-16 | 2025-02-17 | 2025-02-24 | 2025-04-03 | 2025-04-18 | 2025-04-25 | 2025-05-01 | 2025-05-08 | 2025-05-22
2810299.39

## Consulting
Description (Value cannot exceed 250 Characters) | Reference No. | Category - Sourcing | Sourcing Method | Type of Competition | Estimated Amount in US$ | Financed By | Request Submission Date | Advertising Date | Opening Date | Evaluation Date | Approval Date IPC | Opening of Financial Proposal | Combined Evaluation | Approval Date | Contract Vetting | Contract Signing
Hire a consultant to Develop a comprehensive ToR for AfCFTA IT Campus Network for the Installation of Network Infrastructure Solutions, Firewall and Network Access Control | AfCFTA/AHRMD/CS/001 | CS | INDV | OC | 40, 000 | IPs | Q1 | 2025-02-20 | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2025-04-17 | 2025-04-24 | 2025-04-30 | 2025-05-07 | 2025-05-21
Hire a firm to install and implement the proposed IT campus solution on a fix and supply of equipment basis | AfCFTA/AHRMD/CS/002 | CS | OC | OC | 300000 | IPs | Q2 | 2025-04-02 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-07-04
Initial Consultant to conduct quality control and overall monitoring of the project until the project is fully completed | AfCFTA/AHRMD/CS/003 | CS | INDV | OC | 10, 000 | IPs | Q2 | 2025-04-04 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-07-07
Hiring of SharePoint developer for AfCFTA Library and Record keeping | AfCFTA/AHRMD/CS/004 | CS | INDV | OC | 50000 | PAI | Q1 | 2025-02-21 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-23
Hiring Records Management officer for scanning campaigns | AfCFTA/AHRMD/CS/005 | CS | INDV | OC | 28955.24 | PAI | Q2 | 2025-04-08 | 2025-05-08 | 2025-05-15 | 2025-05-22 | 2025-06-05 | 2025-06-12 | 2025-06-19 | 2025-06-26 | 2025-07-10
Hiring a consultancy firm for business improvement | AfCFTA/AHRMD/CS/007 | CS | INDV | OC | 30000 | IPs | Q3 | 2025-07-07 | 2025-08-07 | 2025-08-14 | 2025-08-21 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-09
Hiring a facilitator for Continuous Improvement Culture: Foster a culture of continuous improvement through regular feedback and innovation sessions | AfCFTA/AHRMD/CS/008 | CS | INDV | OC | 10000 | IPs | Q3 | 2025-07-11 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-13
Hire a consultant to Integrate privacy considerations into the design and development of all IT systems and processes and Implement a zero-trust security model to enhance data protection | AfCFTA/AHRMD/CS/009 | CS | INDV | OC | 15000 | MS | Q2 | 2025-04-10 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-14
Hire a consultant to develop writting test with online correction/ Use AI to screen resumes, conduct initial interviews, and match candidates with job requirements. | AfCFTA/AHRMD/CS/010 | CS | INDV | OC | 58328.38 | IPs | Q1 | 2025-02-25 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-27
Hiring a individual consulting for MBRS improvement (onboarding and offboarding) | AfCFTA/AHRMD/CS/011 | CS | INDV | OC | 6000 | MS | Q3 | 2025-07-14 | 2025-08-14 | 2025-08-21 | 2025-08-28 | 2025-09-11 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-17
Hiring a individual Consultant to develop comprehensive onboarding programs using interactive and immersive technologies. | AfCFTA/AHRMD/CS/012 | CS | INDV | OC | 4000 | MS | Q3 | 2025-07-21 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-23
Hiring of SharePoint developer for additional features in the AHRMD Plateform (ACCESS)/ Employee Self-Service Portals | AfCFTA/AHRMD/CS/013 | CS | INDV | OC | 60000 | IPs | Q1 | 2025-02-28 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-04-16 | 2025-04-30
Hiring a individual Consultant for Mobile Access Apps development : Develop mobile applications to provide easy access to HR and administrative services | AfCFTA/AHRMD/CS/014 | CS | INDV | OC | 20000 | IPs | Q3 | 2025-08-04 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-11-06
Hiring a consultant to develop AfCFTA Cultural strategy based on AfCFTA Strategic Plam | AfCFTA/AHRMD/CS/015 | CS | INDV | OC | 90190 | Ips MS | Q3 | 2025-08-11 | 2025-09-11 | 2025-09-19 | 2025-09-26 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-14
Hiring a individual consultant to develop programs to integrate AU institutional culture into daily operations. | AfCFTA/AHRMD/CS/016 | CS | INDV | OC | 25000 | PAI | Q3 | 2025-08-18 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-20
Consultancy Services to procuring E-CO System Developer Company , Inception meeting with identified System Developer Company | AfCFTA/CUSTM/CS/001 | CS | INDV | OC | 30000 | WORLD BANK | June | 2025-06-04 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-09-05
Recruit consultant to conduct study on the maritime transport between African Countries | AfCFTA/CUSTM/CS/003 | CS | INDV | OC | 38324 | BADEA | August | 2025-08-12 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-14
Engage consultant to conduct study on Customs Management Systems | AfCFTA/CUSTM/CS/004 | CS | INDV | OC | 25000 | AfDB | Jan, to Dec. | 2025-01-22 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-28
Develop a monitoring and evaluation mechanism for the AfCFTA Customs Capacity Buidling | AfCFTA/CUSTM/CS/005 | CS | INDV | OC | 108000 | WORLD BANK | March-June | 2025-03-07 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-09
Consultancy Services - technical assistance for two long-term senior experts for the implementation of Competition Policy | AfCFTA/DTIGC/CS/001 | CS | INDV | OC | 150000 | EU/ TAF(100%) | February 2025 | 2025-02-17 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-14 | 2025-04-21 | 2024-04-28 | 2025-05-05 | 2025-05-19
Consultancy Services - technical assistance for four long-term senior experts for the negotiations, finalisation and implementation of the tariff offers- Market Access | AfCFTA/DTIGC/CS/002 | CS | INDV | OC | 400000 | EU/TAF(100%) | February 2025 | 2025-02-26 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-23 | 2025-04-30 | 2025-05-07 | 2025-05-14 | 2025-05-28
Consultancy Services - technical assistance (Trade Specialist) and Working sessions on the alignment of the submitted market access HS 2017 offers to HS2022 | AfCFTA/DTIGC/CS/003 | CS | INDV | OC | 161400 | World Bank | February 2025 | 2025-02-26 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-23 | 2025-04-30 | 2025-05-07 | 2025-05-14 | 2025-09-05
Consultancy Services - technical assistance for two long-term mid-level experts for the negotiation, finalisation and implementation of the tariff offers- Market Access | AfCFTA/DTIGC/CS/004 | CS | INDV | OC | 300000 | EU/TAF(100%) | February 2025 | 2025-02-28 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-30
Consultancy Services - Technical assistance for one key expert to develop continental SEZ Strategy | AfCFTA/DTIGC/CS/005 | CS | INDV | OC | 30000 | EU/TAF(100%) | June 2025 | 2025-06-04 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-09-05
Three (3) Studies on the implementation of tariff offers | AfCFTA/DTIGC/CS/006 | CS | INDV | OC | 180000 | EU/TAF(100%) | February, May September 2025 | 2025-02-28 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-30
Develop advocacy and communication tools on competition policy and law to foster competition culture, raise awareness on the Competition Protocol and educate on the benefit of competition for businesses and consumers in the AfCFTA market | AfCFTA/DTIGC/CS/007 | CS | INDV | OC | 60000 | World Bank | February 2025 | 2025-02-26 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-23 | 2025-04-30 | 2025-05-07 | 2025-05-14 | 2025-05-28
Consultancy Services to Host and Maintain the AfCFTA NTB Online Mechanism | AfCFTA/DTIGC/CS/008 | CS | INDV | OC | 120000 | EU/TAF(100%) | January 2025 | 2025-01-22 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-28
Conduct three (3) studies on competition policy | AfCFTA/DTIGC/CS/009 | CS | INDV | OC | 180000 | EU/WB(100%) | February 2025 | 2025-02-24 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-26
2480197.62

## Sourcing Methods Mapping
Procurement Category Code | GO | CW | CS | NC | Sourcing Category Code | Sourcing Category Definition | Review Type | Type of Competition Code | Sourcing Type of Competition
GO | RFP | RFP | QCBS | RFP | GO | Goods | Post | OC | Open Competition
CW | RFB | RFB | FBS | RFB | W | Works | Prior | LC | Limited Competition
CS | RFQ | RFQ | LCS | RFQ | CS | Consultant Services |  | DC | Direct Competition
NC | DIR | DIR | QBS | DIR | NC | Non-Consulting Services
| UN | UN | CDS | UN
| EA | CDD | INDV | EA | Sourcing Method Code (CS) | Sourcing Method Definition |  | Sourcing Method Code (GO) | Sourcing Method Definition
| IMP | FCA | UN | CDD | QCBS | Quality and Cost-Based Selection |  | RFP | Request for Proposals
| COMM | APA | NPO | FCA | FBS | Fixed Budget Selection |  | RFB | Request for Bids
| CDD | PPP | BANK | APA | LCS | Least Cost Selection |  | RFQ | Request for Quotations
| APA | CP | PRA | PPP | QBS | Quality Based Selection |  | DIR | Direct Selection
| CP |  | CAPA | CP | CQS | Consultant Qualification Selection |  | UN | UN Agencies (Direct)
|  |  | CCP |  | CDS | Direct Selection
[5 empty] | INDV | Individual Consultant Selection
[5 empty] | UN | UN Agencies (Direct)
[5 empty] | PRA | Procurement Agents
[5 empty] | Sourcing Method Code (W) | Procurement Method Definition |  | Sourcing Method Code (NC) | Procurement Method Definition
[5 empty] | RFP | Request for Proposals |  | RFP | Request for Proposals
[5 empty] | RFB | Request for Bids |  | RFB | Request for Bids
[5 empty] | RFQ | Request for Quotations |  | RFQ | Request for Quotations
[5 empty] | DIR | Direct Selection |  | DIR | Direct Selection
[5 empty] | UN | UN Agencies (Direct) |  | UN | UN Agencies (Direct)
[5 empty] | FCA | Force Account |  | FCA | Force Account
[5 empty] | PPP | Public Private Partnerships |  | PPP | Public Private Partnerships